## Template
|  | Akounter |  | Total | Actual | Actual | Planned | Planned
|  | Plan Updated: | 2019-06-30 | 3 | 0 | 0 | 0 | 0% | Tolerance: | time axis 2019-07-01 to 2020-02-06
[9 empty] | 0% | 2019-07-01: WB 1 July; 2019-07-08: WB 8 July; 2019-07-15: WB 15 July; 2019-07-22: WB 22 July; 2019-07-29: WB 29 July; 2019-08-05: WB 5 Aug; 2019-08-12: WB 12 Aug; 2019-08-19: WB 19 Aug; 2019-08-26: WB 26 Aug; 2019-09-02: WB 2 Sep; 2019-09-09: WB 9 Sep; 2019-09-16: WB 16 Sep; 2019-09-23: WB 23 Sep; 2019-09-30: WB 30 Sep; 2019-10-07: WB 7 Oct; 2019-10-14: WB 14 Oct; 2019-10-21: WB 21 Oct; 2019-10-28: WB 28 Oct; 2019-11-04: WB 4 Nov; 2019-11-09: WB 9 Nov; 2019-11-14: WB 14 Nov; 2019-11-19: WB 19 Nov; 2019-11-24: WB 24 Nov; 2019-11-29: WB 29 Nov; 2019-12-04: WB 4 Dec; 2019-12-09: WB 9 Dec; 2019-12-14: WB 14 Dec; 2019-12-19: WB 19 Dec; 2019-12-24: WB 24 Dec; 2019-12-29: WB 29 Dec; 2020-01-03: WB 3 Jan; 2020-01-08: WB 8 Jan; 2020-01-13: WB 13 Jan; 2020-01-18: WB 18 Jan; 2020-01-23: WB 23 Jan; 2020-01-28: WB 28 Jan; 2020-02-02: WB 2 Feb
ID | Resource | Task | Responsibility | Start Date | Number Days | End Date | % Complete | % Planned | Status | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
2.0 |  | Form Design
| Excel | Prepare design on excel | Kamal/Nidhi/Rohit | 2019-07-01 | 2 | 2019-07-02 | 0% | 0% | G | bar: WB 1 July 1 to WB 1 July 2
| Excel | Finalize form design | AA/AA/TS | 2019-07-03 | 3 | 2019-07-05 | 0% | 0% | G | WB 1 July 3: S; WB 1 July 4: X; WB 1 July 5: E
[10 empty] | S | E
Formulas:
Planned = IF(E2<[Total],0,IF(E2>[Actual],1,NETWORKDAYS([Total],E2)/NETWORKDAYS([Total],[Actual])))
Total = [Actual, row above]+1

## SMS
|  | Student Management System |  | Total | Actual | Actual | Planned | Planned
|  | Plan Updated: | 2019-06-30 | 3 | 0 | 0 | 0 | 0% | Tolerance: | time axis 2019-07-01 to 2020-02-06
[9 empty] | 0% | 2019-07-01: WB 1 July; 2019-07-08: WB 8 July; 2019-07-15: WB 15 July; 2019-07-22: WB 22 July; 2019-07-29: WB 29 July; 2019-08-05: WB 5 Aug; 2019-08-12: WB 12 Aug; 2019-08-19: WB 19 Aug; 2019-08-26: WB 26 Aug; 2019-09-02: WB 2 Sep; 2019-09-09: WB 9 Sep; 2019-09-16: WB 16 Sep; 2019-09-23: WB 23 Sep; 2019-09-30: WB 30 Sep; 2019-10-07: WB 7 Oct; 2019-10-14: WB 14 Oct; 2019-10-21: WB 21 Oct; 2019-10-28: WB 28 Oct; 2019-11-04: WB 4 Nov; 2019-11-09: WB 9 Nov; 2019-11-14: WB 14 Nov; 2019-11-19: WB 19 Nov; 2019-11-24: WB 24 Nov; 2019-11-29: WB 29 Nov; 2019-12-04: WB 4 Dec; 2019-12-09: WB 9 Dec; 2019-12-14: WB 14 Dec; 2019-12-19: WB 19 Dec; 2019-12-24: WB 24 Dec; 2019-12-29: WB 29 Dec; 2020-01-03: WB 3 Jan; 2020-01-08: WB 8 Jan; 2020-01-13: WB 13 Jan; 2020-01-18: WB 18 Jan; 2020-01-23: WB 23 Jan; 2020-01-28: WB 28 Jan; 2020-02-02: WB 2 Feb
ID | Resource | Task | Responsibility | Start Date | Number Days | End Date | % Complete | % Planned | Status | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
2.0 |  | Form Design
| Excel | Prepare design on excel | Kamal/Nidhi/Rohit | 2019-07-01 | 2 | 2019-07-02 | 0% | 0% | G | bar: WB 1 July 1 to WB 1 July 2
| Excel | Finalize form design | AA/AA/TS | 2019-07-03 | 3 | 2019-07-05 | 0% | 0% | G | WB 1 July 3: S; WB 1 July 4: X; WB 1 July 5: E
[10 empty] | S | E
Formulas:
Planned = IF(E2<[Total],0,IF(E2>[Actual],1,NETWORKDAYS([Total],E2)/NETWORKDAYS([Total],[Actual])))
Total = [Actual, row above]+1

## MCT
|  | CRM - Inventory |  | Total | Actual | Actual | Planned | Planned
|  | Plan Updated: | 2019-06-30 | 0 | 0 | #DIV/0! | 0 | #DIV/0! | Tolerance: | time axis 2019-07-01 to 2020-02-06
[9 empty] | 0% | 2019-07-01: WB 1 July; 2019-07-08: WB 8 July; 2019-07-15: WB 15 July; 2019-07-22: WB 22 July; 2019-07-29: WB 29 July; 2019-08-05: WB 5 Aug; 2019-08-12: WB 12 Aug; 2019-08-19: WB 19 Aug; 2019-08-26: WB 26 Aug; 2019-09-02: WB 2 Sep; 2019-09-09: WB 9 Sep; 2019-09-16: WB 16 Sep; 2019-09-23: WB 23 Sep; 2019-09-30: WB 30 Sep; 2019-10-07: WB 7 Oct; 2019-10-14: WB 14 Oct; 2019-10-21: WB 21 Oct; 2019-10-28: WB 28 Oct; 2019-11-04: WB 4 Nov; 2019-11-09: WB 9 Nov; 2019-11-14: WB 14 Nov; 2019-11-19: WB 19 Nov; 2019-11-24: WB 24 Nov; 2019-11-29: WB 29 Nov; 2019-12-04: WB 4 Dec; 2019-12-09: WB 9 Dec; 2019-12-14: WB 14 Dec; 2019-12-19: WB 19 Dec; 2019-12-24: WB 24 Dec; 2019-12-29: WB 29 Dec; 2020-01-03: WB 3 Jan; 2020-01-08: WB 8 Jan; 2020-01-13: WB 13 Jan; 2020-01-18: WB 18 Jan; 2020-01-23: WB 23 Jan; 2020-01-28: WB 28 Jan; 2020-02-02: WB 2 Feb
ID | Resource | Task | Responsibility | Start Date | Number Days | End Date | % Complete | % Planned | Status | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
2.0 |  | Design
| Excel | Prepare list of functionalities CRM and inventory | Gaurav/Kamal | 2019-07-01 | 3 | 2019-07-03 | 0% | 0% | G | WB 1 July 1: S; WB 1 July 2: X; WB 1 July 3: E
| Excel | Prepare templates/Forms | Gaurav/Kamal | 2019-07-01 | 3 | 2019-07-03 | 0% | 0% | G | WB 1 July 1: S; WB 1 July 2: X; WB 1 July 3: E
| Excel | Connection to Akounter | Gaurav/Kamal | 2019-07-01 | 3 | 2019-07-03 | 0% | 0% | G | WB 1 July 1: S; WB 1 July 2: X; WB 1 July 3: E
| SQL | Prepare database | Gaurav/Kamal | 2019-07-01 | 3 | 2019-07-03 | 0% | 0% | G | WB 1 July 1: S; WB 1 July 2: X; WB 1 July 3: E
2.0 |  | Business Catch-up
|  | Visit MCT | Kamal/Rohit | 2019-07-04 | 1 | 2019-07-05 | 0% | 0% | G | bar: WB 1 July 4 to WB 1 July 5
| Excel | Update list of functionalities & design | Kamal | 2019-07-05 | 3 | 2019-07-09 | 0% | 0% | G | WB 1 July 5: S; WB 8 July 8: X; WB 8 July 9: E
2.0 |  | Design Review
|  | Review Meeting with TS/AA/AA | Gaurav/Kamal/TS | 2019-07-05 | 1 | 2019-07-08 | 0% | 0% | G | bar: WB 1 July 5 to WB 8 July 8
2.0 |  | CRM - Build
2.0 |  | Inventory - Build
Formulas:
Planned = IF(E2<[Total],0,IF(E2>[Actual],1,NETWORKDAYS([Total],E2)/NETWORKDAYS([Total],[Actual])))
Total = [Actual, row above]

## Akounter
|  | Akounter |  | Total | Actual | Actual | Planned | Planned
|  | Plan Updated: | 2019-06-30 | 3 | 0 | 0 | 0 | 0% | Tolerance: | time axis 2019-07-01 to 2020-02-06
[9 empty] | 0% | 2019-07-01: WB 1 July; 2019-07-08: WB 8 July; 2019-07-15: WB 15 July; 2019-07-22: WB 22 July; 2019-07-29: WB 29 July; 2019-08-05: WB 5 Aug; 2019-08-12: WB 12 Aug; 2019-08-19: WB 19 Aug; 2019-08-26: WB 26 Aug; 2019-09-02: WB 2 Sep; 2019-09-09: WB 9 Sep; 2019-09-16: WB 16 Sep; 2019-09-23: WB 23 Sep; 2019-09-30: WB 30 Sep; 2019-10-07: WB 7 Oct; 2019-10-14: WB 14 Oct; 2019-10-21: WB 21 Oct; 2019-10-28: WB 28 Oct; 2019-11-04: WB 4 Nov; 2019-11-09: WB 9 Nov; 2019-11-14: WB 14 Nov; 2019-11-19: WB 19 Nov; 2019-11-24: WB 24 Nov; 2019-11-29: WB 29 Nov; 2019-12-04: WB 4 Dec; 2019-12-09: WB 9 Dec; 2019-12-14: WB 14 Dec; 2019-12-19: WB 19 Dec; 2019-12-24: WB 24 Dec; 2019-12-29: WB 29 Dec; 2020-01-03: WB 3 Jan; 2020-01-08: WB 8 Jan; 2020-01-13: WB 13 Jan; 2020-01-18: WB 18 Jan; 2020-01-23: WB 23 Jan; 2020-01-28: WB 28 Jan; 2020-02-02: WB 2 Feb
ID | Resource | Task | Responsibility | Start Date | Number Days | End Date | % Complete | % Planned | Status | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6
2.0 |  | Form Design
| Excel | Prepare design on excel | Kamal/Nidhi/Rohit | 2019-07-01 | 2 | 2019-07-02 | 0% | 0% | G | bar: WB 1 July 1 to WB 1 July 2
| Excel | Finalize form design | AA/AA/TS | 2019-07-03 | 3 | 2019-07-05 | 0% | 0% | G | WB 1 July 3: S; WB 1 July 4: X; WB 1 July 5: E
2.0 |  | Invoicing
| Django | Printing of Invoice | Kamal | 2019-07-01 | 1 | 2019-07-02 | 0% | 0% | G | bar: WB 1 July 1 to WB 1 July 2
| Django | Multiple final Invoice against single PO | Kamal | 2019-07-01 | 2 | 2019-07-02 | 0% | 0% | G | bar: WB 1 July 1 to WB 1 July 2
| Django | PO being reduced by amount of Final invoice | Kamal | 2019-07-03 | 2 | 2019-07-04 | 0% | 0% | G | bar: WB 1 July 3 to WB 1 July 4
| Django | Final Invoice duplication | Kamal | 2019-07-04 | 2 | 2019-07-05 | 0% | 0% | G | bar: WB 1 July 4 to WB 1 July 5
| Test | Testing | Vivek | 2019-07-08 | 1 | 2019-07-09 | 0% | 0% | G | bar: WB 8 July 8 to WB 8 July 9
2.0 |  | Data Setup
| Tally | Export 20 different entries from Tally | Satya | 2019-07-02 | 1 | 2019-07-03 | 0% | 0% | G | bar: WB 1 July 2 to WB 1 July 3
| Excel | Setup same entries | Nidhi | 2019-07-03 | 1 | 2019-07-04 | 0% | 0% | G | bar: WB 1 July 3 to WB 1 July 4
| Website | Setup same entries | Nidhi | 2019-07-03 | 1 | 2019-07-04 | 0% | 0% | G | bar: WB 1 July 3 to WB 1 July 4
2.0 |  | Reporting
| Django | Ledger View | Vivek/Nidhi | 2019-07-01 | 1 | 2019-07-02 | 0% | 0% | G | bar: WB 1 July 1 to WB 1 July 2
| Test | Testing of the Ledger View | Rohit/Raghav | 2019-07-03 | 1 | 2019-07-04 | 0% | 0% | G | bar: WB 1 July 3 to WB 1 July 4
| Test | Testing of the Chart of Account | Rohit/Raghav | 2019-07-03 | 1 | 2019-07-04 | 0% | 0% | G | bar: WB 1 July 3 to WB 1 July 4
| Test | Testing of the Day Book | Rohit/Raghav | 2019-07-03 | 1 | 2019-07-04 | 0% | 0% | G | bar: WB 1 July 3 to WB 1 July 4
| Django | Balance Sheet | Vivek/Nidhi | 2019-07-02 | 1 | 2019-07-03 | 0% | 0% | G | bar: WB 1 July 2 to WB 1 July 3
| Test | Testing of the Balance Sheet | Rohit/Raghav | 2019-07-04 | 1 | 2019-07-05 | 0% | 0% | G | bar: WB 1 July 4 to WB 1 July 5
| Django | Trial Balance | Vivek/Nidhi | 2019-07-03 | 1 | 2019-07-04 | 0% | 0% | G | bar: WB 1 July 3 to WB 1 July 4
| Test | Testing of the Trial Balance | Rohit/Raghav | 2019-07-04 | 1 | 2019-07-05 | 0% | 0% | G | bar: WB 1 July 4 to WB 1 July 5
| Django | PnL | Vivek/Nidhi | 2019-07-04 | 1 | 2019-07-05 | 0% | 0% | G | bar: WB 1 July 4 to WB 1 July 5
| Test | Testing of the PnL | Rohit/Raghav | 2019-07-08 | 1 | 2019-07-09 | 0% | 0% | G | bar: WB 8 July 8 to WB 8 July 9
2.0 |  | Form Built
| Django | Expense/Revenue/Others | Nidhi | 2019-07-08 | 3 | 2019-07-10 | 0% | 0% | G | WB 8 July 8: S; WB 8 July 9: X; WB 8 July 10: E
| Test | Testing of the forms | Rohit/Raghav | 2019-07-11 | 2 | 2019-07-12 | 0% | 0% | G | bar: WB 8 July 11 to WB 8 July 12
| Test | Testing of the Calculations | Vivek/Rohit | 2019-07-15 | 2 | 2019-07-16 | 0% | 0% | G | bar: WB 15 July 15 to WB 15 July 16
2.0 |  | Import to Tally
| Tally | Testing of the entries | Nidhi/Vivek | 2019-07-16 | 3 | 2019-07-18 | 0% | 0% | G | WB 15 July 16: S; WB 15 July 17: X; WB 15 July 18: E
| Django | Develop | Nidhi/Vivek | 2019-07-19 | 2 | 2019-07-22 | 0% | 0% | G | bar: WB 15 July 19 to WB 22 July 22
[10 empty] | S | E
Formulas:
Planned = IF(E2<[Total],0,IF(E2>[Actual],1,NETWORKDAYS([Total],E2)/NETWORKDAYS([Total],[Actual])))
Total = [Actual, row above]+1
Total = [Total, row above]

## Months (hidden)
1 | Jan
2 | Feb
3 | Mar
4 | Apr
5 | May
6 | June
7 | July
8 | Aug
9 | Sep
10 | Oct
11 | Nov
12 | Dec